## Current Iteration
|  | Iteration Number: |  |  |  | 5
|  | Expected Total effort: |  |  |  | 530
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) |  |  |  |  | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | Task Balance | Percentage Completed
Sharepoint configuration | 5 | 5 | 1 | 0 | 0 | 0 | -1 | 120%
Enquire page | 92 | 17 | 20 | 24 | 20 | 16 | -5 | 105.4%
home page, about page | 63 | 24 | 28 | 11 | 3 | 0 | -3 | 104.8%
Success stories page | 59 | 0 | 0 | 22 | 30 | 11 | -4 | 106.8%
Courses page | 60 | 24 | 26 | 11 | 6 | 0 | -7 | 111.7%
Contacts page | 50 | 0 | 1 | 28 | 29 | 7 | -15 | 130%
News page | 64 | 24 | 25 | 18 | 1 | 0 | -4 | 106.2%
Research page | 53 | 0 | 0 | 12 | 28 | 14 | -1 | 101.9%
Register Alumni page | 84 | 23 | 30 | 28 | 14 | 4 | -15 | 117.9%
Effort Remaining | 530 | 413 | 282 | 128 | -3 | -55 | -55 | 110.4%
Ideal Trend | 530 | 424 | 318 | 212 | 106 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days